## Sheet1
Technical Assessment
Simple HTTP WebServer in Java
# | Type | Description | Effort | Done?
1 | Configuration | Setup Github Repo | 1 | ü
2 | Configuration | Setup Dockerfile | 1 | ü
3 | Configuration | Setup Maven Project (Pom.xml) | 1 | ü
4 | Analysis | Draft the application and UML diagrams (Class, Use case, State Machine) | 8 | ü
5 | Development | Implement WebServer in Java SE 8 |  | ü
5.1a | Development | * Implement Socket handling | 2 | ü
5.1b | Testing | * Unit Test Socket Handling | 2 | ü
5.2a | Development | * Parse request and serve response | 2 | ü
5.2b | Testing | * Unit Test requests and response | 2 | ü
5.3a | Development | * Handle GET requests | 2 | ü
5.3b | Testing | * Unit Test GET requests | 2 | ü
5.4a | Development | * Handle HEAD requests | 2 | ü
5.4b | Testing | * Unit Test HEAD requests | 2 | ü
5.5a | Development | * Serve files and subdirectories | 3 | ü
5.5b | Testing | * Unit Test files and subdirectories | 3 | ü
5.6a | Development | * Implement Etag | 5 | ü
5.6b | Testing | * Unit test Etag | 5 | ü
5.7a | Development | * Implement multithreading | 5 | ü
5.7b | Testing | * Unit test multithreading | 5 | ¡
6 | Testing | API Testing | 8 | ü
7 | Profiling | Profile written code + potential Refactoring | 2 | ¡
8 | Testing | Running Loadtests with JMeter and generate Report for various metrics | 2 | ¡
9 | Documentation | Generate Javadoc Documentation | 1 | ü
10 | Documentation | Create Readme | 1 | ü
10 | Delivery | Generate docker image and push final package and send in for review | 1 | ü
|  | Sum of all efforts | 68
|  | Capacity per day | 10
|  | Sum of all efforts / Capacity per day | 6.8
|  | Buffer = 1 day | 7.8
|  | 7th October + 8 days + 2 days weekend | Tuesday, 19th October
Note: Regular commits will be done where appropriate. Order might not be strictly chronological.